## Dummydata
Project Phase | Task | Employee | Start Date | End Date | Progress (%) | Time Grouping
Initiation | Define Project Scope | John Doe | 2025-05-01 | 2025-05-03 | 60 | Week
Initiation | Identify Stakeholders | Jane Smith | 2025-05-02 | 2025-05-04 | 85
Initiation | Conduct Feasibility Study | Peter Jones | 2025-05-03 | 2025-05-07 | 40
Initiation | Secure Project Funding | Alice Brown | 2025-05-05 | 2025-05-08 | 95
Initiation | Project Kick-off Meeting | John Doe | 2025-05-08 | 2025-05-08 | 100
Planning | Develop Project Plan | Jane Smith | 2025-05-09 | 2025-05-12 | 30
Planning | Define Task Dependencies | Peter Jones | 2025-05-10 | 2025-05-13 | 70
Planning | Allocate Resources | Alice Brown | 2025-05-12 | 2025-05-15 | 55
Planning | Finalize Budget | John Doe | 2025-05-14 | 2025-05-16 | 80
Planning | Risk Assessment | Jane Smith | 2025-05-16 | 2025-05-18 | 25
Execution | Task A Implementation | Peter Jones | 2025-05-19 | 2025-05-23 | 45
Execution | Task B Development | Alice Brown | 2025-05-20 | 2025-05-25 | 65
Execution | Task C Testing | John Doe | 2025-05-24 | 2025-05-27 | 90
Execution | Task D Integration | Jane Smith | 2025-05-26 | 2025-05-30 | 35
Execution | User Training | Peter Jones | 2025-05-29 | 2025-06-02 | 75
Closure | Final Report Generation | Alice Brown | 2025-06-02 | 2025-06-04 | 80
Closure | Stakeholder Sign-off | John Doe | 2025-06-03 | 2025-06-05 | 95
Closure | Project Documentation Archive | Jane Smith | 2025-06-05 | 2025-06-06 | 50
Closure | Lessons Learned Session | Peter Jones | 2025-06-06 | 2025-06-07 | 100
Closure | Project Closure Meeting | Alice Brown | 2025-06-08 | 2025-06-09 | 100

## python
#VALUE!
#VALUE!